## Fixed Price BOT
Appendix D - Attachment A-2 Wind BOT Cost Components
| Wind Only Total | Wind + Battery Option 1 ( __ MW) | Wind + Battery Option 2 ( __ MW) | Wind + Battery Option 3 ( __ MW)
COMPONENT COSTS REQUIRED
Generation Equipment & Tech.
Turbine Generator | $ | $ | $ | $
Rotor and Blades | $ | $ | $ | $
Gearbox | $ | $ | $ | $
Tower | $ | $ | $ | $
Other Major Equipment | $ | $ | $ | $
Mechanical & Elec. Equip.
Switchgear | $ | $ | $ | $
Mechanical Brake | $ | $ | $ | $
Power Converter | $ | $ | $ | $
Instrumentation & Controls
Controller | $ | $ | $ | $
Pitch System | $ | $ | $ | $
Yaw System | $ | $ | $ | $
Medium Voltage Collection System
Wiring - AC / Terminations | $ | $ | $ | $
MV substation | $ | $ | $ | $
Site Work
Site Work / Roads / Fencing | $ | $ | $ | $
Labor Cost
Construction labor | $ | $ | $ | $
MISO Transmission Cost
Interconnection facilities | $ | $ | $ | $
Estimated Network Upgrades (NU) Cost | $ | $ | $ | $
Estimated Stand-Alone Network Upgrades (SANU) Cost | $ | $ | $ | $
Transmission Owner Interconnection Facility (TOIF) Cost | $ | $ | $ | $
Affected System Upgrade Cost | $ | $ | $ | $
Other Work and Costs
Engineering | $ | $ | $ | $
Permitting | $ | $ | $ | $
Other Items / Contingency | $ | $ | $ | $
Indirects | $ | $ | $ | $
Balance of Plant | $ | $ | $ | $
Land Purchase Cost / Price (if applicable) | $ | $ | $ | $
Battery Energy Storage System (BESS) - (if applicable)
Batteries | $ | $ | $ | $
Inverter/Transformer Skids (if applicable) | $ | $ | $ | $
Enclosures | $ | $ | $ | $
Balance of System | $ | $ | $ | $
Total Acquisition Cost | 0 | 0 | 0 | 0
Provide the accuracy of the project cost estimate using an appropriate cost estimate classification system (e.g., Class 1 through Class 5) for both the Wind resource and the BESS option, if applicable. Note: Proposal project cost estimate should be based on front-end engineering from a qualified external and/or internal source that supports at least a Class 3 (as defined by AACE standards) cost estimate (-20% to +30%).
Describe how the estimate(s) were developed (e.g., third-party engineering firm, in-house, vendor supplied bids, etc.).